City University of Hong Kong

CS3343 Software Engineering Practice

Group 21

Project Plan

Project Title: Roguelike Card Game

| Name | Student Number |
| --- | --- |
| Shek King Fung | 58527549 |
| Cheung Tin Yeung | 58582747 |
| Kwok Hang Wai | 58534079 |
| Ho Chun Hin | 58551795 |
| Lam Shi Ho | 58541347 |
| Yip Hiu Hong | 58539340 |

Table of Contents

1. Project Description	3

2. Objective of the project	3

3. Stakeholders	3

4. Constraints	4

4.1. Scope	4

4.2. Time	4

4.3. Cost	4

5. Project Team Organization	4

6. Software Development Methodology	4

7. Developments Tools	5

8. Software Configuration	5

8.1. Change Control	5

8.2. Version Control	5

9. Work Breakdown Structure	5

10. Activity Diagrams	6

- Project Description

This game project is a strategic roguelite that takes elements from traditional Role-Playing Games (RPG), Poker, and the roguelite genre to combine them together. The gameplay will be built around using different types of poker hands to score and complete. Players may also obtain items or relics that enhance their poker hand as the rounds get progressively harder.

- Objective of the project

The objective of this project is to create a singleplayer game with high replayability and easy to understand mechanics, allowing players from different age groups to enjoy a unique experience within each playthrough. The following features are set to help achieve the objective.

- Poker hand combat system: The core combat will revolve around a poker hand based system where players draw cards to form traditional poker hands which will determine the score obtained (e.g. Pairs < Straights < Royal Flushes). This provides a strategic gameplay but also an easy to understand combat mechanic.

- In-game stores and Deck building: The gear obtained by the player after several stages are randomized. The players will have to adapt to what they get within the stores to make a sustainable “build” to survive through the stages, it will also be the main way the player gets stronger. And to minimize the randomness and frustration of making a specific poker hand, players will be able to further add or decrease cards from their decks to their liking using items in the store as well.

- Difficulty scaling: To keep players from powering through stages of the game and making content feel underwhelming, the enemies faced by the player will progressively get stronger after each stage.

- Stakeholders

| Stakeholders | Description |
| --- | --- |
| Play Testers | Provides gameplay requirements and feedback to the project team |
| Developers | Developers is required to develop the software |
| Project manager | Project management |

- Constraints

  - Scope

The base requirement for the game is mostly defined but it will be subject to change through iterations and playtesting. Due to game balancing and gameplay flow developers may have to communicate with playtesters back and forth to find the perfect balance which could be time consuming, this may also delay the release of the game or even worse, result in failure and abandonment of the project.

  - Time

The duration planned for this project is 13 weeks, which is relatively tight. Furthermore, there is no room for extension. Therefore, the project scope and cost may be adjusted to meet the time requirements.

  - Cost

Since this game project doesn't ultimately need to be released to the public and the team members are not professional game developers, there is no additional budget for purchasing development tools. All work will be done using free and suitable development tools.

- Project Team Organization

| Name | Position |
| --- | --- |
| Shek King Fung | Testing engineers |
| Cheung Tin Yeung | Bugging engineers |
| Kwok Hang Wai | Developers |
| Ho Chun Hin | Developers |
| Lam Shi Ho | Developing Analyst |
| Yip Hiu Hong | Project Manager |

- Software Development Methodology

Prototype methodology is used for software development, as it helps us to identify the requirements better and can be developed quickly. After developing a prototype, we adjust the code to meet the requirement better and finally start testing and debugging.

- Developments Tools

| Tool | Usage |
| --- | --- |
| Eclipse IDE | Main application for the development of the game |
| JUnit 5 | Program Testing |
| EclEmma | Test Coverage Checking |
| GitHub | Version Control |
| GitHub | Writing Bug Report |

- Software Configuration

  - Change Control

Any changes made on software (e.g. error correction, value change, functionality change) will be logged down. Changes made on the code will also be reviewed by the developers before pushing out the changes.

  - Version Control

changes or iterations of the software will be logged in versions, allowing the project team to review changes or even revert changes depending on the status of the software.

- Work Breakdown Structure

- Stage 1

  - Project Management

  - Task Defining

  - Requirements Defining

  - Analysis & Design

- Stage 2

  - Software Development

    - Core combat system (Poker hands, enemy combat)

    - Core mechanics (+ / - cards, shops, items)

    - Gameplay loop (stage advancing)

    - Roguelite element (random seed generation)

- Stage 3

  - Playtesting

  - Game balancing

  - Debugging

  - Refractoring

  - Production

- Activity Diagrams

| Task | Duration | Start Date | End Date |
| --- | --- | --- | --- |
| 1.0 Stage 1 | 25 days | 5/9/2025 | 30/9/2025 |
| 1.1 Project Management | 8 days | 5/9/2025 | 12/9/2025 |
| 1.2 Task Defining | 3 days | 13/9/2025 | 15/9/2025 |
| 1.3 Requirements Defining | 4 days | 16/9/2025 | 19/9/2025 |
| 1.4 Analysis & Design | 11 days | 20/9/2025 | 30/9/2025 |
| 2.0 Stage 2 | 21 days | 1/10/2025 | 21/10/2025 |
| 2.1 Software Development | 21 days | 1/10/2025 | 21/10/2025 |
| 2.1.1 Core combat system (Poker hands, enemy combat) | 5 days | 1/10/2025 | 5/10/2025 |
| 2.1.2 Core mechanics (+ / - cards, shops, items) | 5 days | 6/10/2025 | 10/10/2025 |
| 2.1.3 Gameplay loop (stage advancing) | 5 days | 11/10/2025 | 15/10/2025 |
| 2.1.4 Roguelite element (random seed generation) | 6 days | 16/10/2025 | 21/10/2025 |
| 3.0 Stage 3 | 31 days | 22/10/2025 | 22/11/2025 |
| 3.1 Playtesting | 7 days | 22/10/2025 | 28/10/2025 |
| 3.2 Game balancing | 5 days | 29/10/2025 | 2/11/2025 |
| 3.3 Debugging | 11 days | 3/11/2025 | 13/11/2025 |
| 3.4 Refractoring | 5 days | 14/11/2025 | 18/11/2025 |
| 3.5 Production | 4 days | 19/11/2025 | 22/11/2025 |